## v1
Document Type: | Inceptive Requirements Traceability Matrix (iRTM)
Project ID: | SmartReplenish-2026
Project name: | ValuPrice Grocery Inventory Management App
Document date: | 2026-03-06
Version: | 1
Assumption(s): | From L0 R-Tree; Precursor to entire new software development for ValuPrice customer-facing inventory management
Constraint(s): | From L0 R-Tree; Budget SGD 380,000; Soft launch target Q3 2026; Azure Singapore region mandatory
Regulation(s): | From L0 R-Tree; Singapore PDPA compliance required for all customer data handling
Serial No. | PS |  |  |  |  | SRS
| Category | ID | Description | Stakeholder | Precedence | Category | ID | Description | Owner | Ranking
1 | Biz Ops | BR-01 | Profiles must link to a ValuPrice Loyalty ID | ValuPrice Project Lead | Essential | Functional | FR-01 | Profiles must link to a ValuPrice Loyalty ID | ValuPrice Project Lead | Must-have
2 | Biz Ops | BR-02 | Support item entry via barcode scanning | ValuPrice Project Lead | Essential | Functional | FR-02 | Convert 1D barcode images into actionable item data | ValuPrice Project Lead | Must-have
3 | Biz Ops | BR-03 | Enable manual search for non-barcoded items | ValuPrice Project Lead | Desirable | Functional | FR-03 | Enforce item categorization using a predefined taxonomy | ValuPrice Project Lead | Must-have
4 | Biz Ops | BR-04 | Provide a +/- interface for stock updates | ValuPrice Project Lead | Essential | Functional | FR-04 | Provide a +/- interface for stock updates | ValuPrice Project Lead | Must-have
5 | Biz Ops | BR-05 | Trigger notifications based on user-defined stock thresholds | ValuPrice Project Lead | Essential | Functional | FR-05 | Trigger notifications based on user-set replenishment levels | ValuPrice Project Lead | Should-have
6 | Biz Ops | BR-06 | Track expiry dates and send "consume soon" alerts | ValuPrice Project Lead | Desirable | Functional | FR-06 | Alert users to expiring items based on category timelines | ValuPrice Project Lead | Should-have
7 | Biz Ops | BR-07 | Auto-generate shopping lists for low-stock items | ValuPrice Project Lead | Essential | Functional | FR-07 | Auto-generate shopping lists for low-stock items | ValuPrice Project Lead | Must-have
8 | Biz Ops | BR-08 | Display item prices and total estimated cost | ValuPrice Project Lead | Desirable | Functional | FR-08 | Show real-time prices with cached offline fallback | ValuPrice Project Lead | Should-have
9 | Biz Ops | BR-09 | Suggest alternatives for "High Risk" out-of-stock items | ValuPrice Project Lead | Acceptable | - | - | Not implemented in current SRS scope | - | -
10 | Biz Ops | BR-10 | Provide self-service account recovery | ValuPrice Project Lead | Essential | Functional | FR-09 | Deliver time-sensitive recovery tokens to registered email addresses | ValuPrice Project Lead | Must-have
11 | IT tech | TR-01 | Host on Microsoft Azure (Singapore) for compliance/low latency | ValuPrice Project Lead | Essential | Non-Functional | NFR-01 | Host on Azure (Singapore) for compliance and speed | ValuPrice Project Lead | Must-have
12 | IT tech | TR-02 | Use Cloud-Native RESTful architecture for sync | ValuPrice Project Lead | Essential | Non-Functional | NFR-02 | Use Cloud-Native RESTful architecture for sync | ValuPrice Project Lead | Must-have
13 | IT tech | TR-03 | Use Azure SQL with daily backups/PITR | ValuPrice Project Lead | Essential | Non-Functional | NFR-03 | Use Azure SQL Standard with bounded auto-scaling | ValuPrice Project Lead | Must-have
14 | IT tech | TR-04 | Use hyperscale/serverless DB for auto-scaling | ValuPrice Project Lead | Desirable | Non-Functional | NFR-03 | Merged into TR-03 as NFR-03 | ValuPrice Project Lead | Must-have
15 | IT tech | TR-05 | Native Android app compatible with v6.0 (API 23)+ | ValuPrice Project Lead | Essential | Non-Functional | NFR-04 | Native Android app supporting version 6.0 (API 23)+ | ValuPrice Project Lead | Must-have
16 | IT tech | TR-06 | Develop in Java/XML for maintainability | ValuPrice Project Lead | Desirable | Non-Functional | NFR-05 | Develop using Kotlin and XML layouts | ValuPrice Project Lead | Must-have
17 | IT tech | TR-07 | Support 1D/2D barcode scanning via camera hardware | ValuPrice Project Lead | Desirable | Functional | FR-10 | Direct interface with the device camera to enable scanning | ValuPrice Project Lead | Must-have
18 | IT tech | TR-08 | Integrate GS1 API for automatic product data population | ValuPrice Project Lead | Acceptable | - | - | Interpreted into FR-02/FR-10 implementation scope | - | -
19 | IT tech | TR-09 | Implement local caching for offline inventory editing | ValuPrice Project Lead | Desirable | Functional | FR-11 | Support offline inventory viewing via local caching | ValuPrice Project Lead | Must-have
20 | IT tech | TR-10 | Comply PDPA using AES-256 and TLS 1.2+ encryption | ValuPrice Project Lead | Essential | Non-Functional | NFR-06 | Comply with PDPA using AES-256 and TLS 1.2+ encryption | ValuPrice Project Lead | Must-have
21 | IT tech | TR-11 | Provide a web-based admin dashboard for catalog/user management | ValuPrice Project Lead | Acceptable | Functional | FR-12 | Provide a secure web dashboard for catalog/user admin | ValuPrice Project Lead | Could-have
22 | IT tech | TR-12 | Deliver OpenAPI/Swagger docs and architecture diagrams | ValuPrice Project Lead | Acceptable | Non-Functional | NFR-07 | Auto-generate technical documentation from code artifacts | ValuPrice Project Lead | Could-have
23 | IT tech | TR-13 | Use secure, time-limited tokens for password resets | ValuPrice Project Lead | Essential | Functional | FR-13 | Secure all reset processes using industry-standard encryption and unique tokens | ValuPrice Project Lead | Must-Have